## schedule
Wk | Date | Task | h | Product | Deadline | Feedback on
1 | 1 Jan | Read literature |  | Thesis agreement | 2 Jan
2 | 8 Jan
3 | 15 Jan |  |  | Draft research proposal | 19 Jan | Draft research proposal
4 | 23 Jan |  |  | Final research proposal
Proposal presentation
Collect discharge data
|  | Collect discharge data |  | Introduction
Collect discharge data
|  | Collect discharge data |  | Field site and data |  | Discharge data
|  | Analyse rainfall input |  | Methods - part x |  | Rainfall data
Process discharge data
Methods - part x
Calibrate model
|  | Calibrate model |  |  |  | Calibrated model
|  | Analyse low flows |  | Results - part x |  | Low flow analyses
Results - part x
Discussion
Conclusion
Abstract
|  |  |  | Full draft report |  | Draft report
Colloquium presentation
All
Total (1008) |  | 0
Use different lines for different tasks. Estimate the time necessary for each task in hours. The total should sum up to 28*36=1008 hours (28 hours per credit, 36 credits).
Be as specific as possible: mention when you will collect which data /do which model runs / write which parts of the report. It often helps to link activities and products to your sub-questions. A specific planning can help later on to see if you are on schedule or that you should e.g. shorten a certain data-processing step or stop calibrating your model, so you have enough time to do the analyses and answer your research questions.
Some fields are filled in as example, but please change, remove or move them such that it fits your own project and planning.
Add lines when necessary. Remove empty ones.
To print to file: Select the cells in the table. File > print > select "print to pdf", "print selection", "narrow margins" and "fit columns on one sheet".
Save the printed pdf in the figs-subfolder (so LaTeX can find it).